## Sheet1
As a | I want to | So that | Estimate
Developer | Consume the web service | I can develop customer facing features | 5
Developer | Consume the web service | I can develop administer facing features | 3
Developer | Connect to the database from the web service | I can persist information about users and their blogs | 2
Customer | Log into the web site | I can do what I'm allowed to do on the website | 3
Customer | See blog posts | I can read them | 3
Customer | Post a blog | I can upload content | 3
Customer | Edit my own blogs | I can change erroneous content | 3
Customer | Navigate the blogs | I can see a list of blog posts and navigate to them | 3
Customer | See the comments on a blog post | I can see what people are saying about my blogs | 8
Customer | Post a comment | I can respond to blog content | 5
Customer | Log out from the web site | I can protect my account | 3
Admin | Disable accounts | I can disable unwanted users | 5
Customer | Register | I can use the website | 3
Admin | Log into the admin website | I can do what I'm allowed to do on the website | 2
Admin | Log out from the admin website | I can protect my account | 3
Admin | Reset customer passwords | I can allow customers to log in again when they've forgotten their credentials | 1
Admin | Disable blogs | I can stop unwanted blogs and their comments being displayed | 5
Admin | Create another admin | I can share my workload | 3
Admin | Change my password | I can keep my account secure | 1